## Sheet1
Requirements Traceability Matrix
Project Name: | AngSalitaNgDiyos.com Liturgical Site
Project Type: | Website
Project Start Date: | 2015-01-12
Project End Date: | 2015-04-12
Project Adviser/s: | Mr. Joe Gene Quesada (Software Development)
Mr. Allan B. Cotecson (Quality Assurance)
Mr. Ernesto Boydon (Software Engineering)
Ms. Ma. Theresa Montemayor (Database Design and Management)
Project Manager: | Joshua C. Dimapilis
Requirement ID | Requirement Description | Requirement Type | Status | Priority | Software Module | Test Case Number | Tested In | Implemented In | Verification
A. SYSTEM REQUIREMENTS
001 | Provides a login page so that registered users can access the site | Needed | In Progress | Medium | Login
002 | Allows unregistered users to sign up for membership | Needed | In Progress | Medium | Login
003 | Allows registered users (admin or member roles) to view the calendar and calendar events | Highly Needed | In Progress | High | Calendar
004 | Does not allow unregistered users to view the calendar and calendar events | Needed | In Progress | Medium | Login
005 | Allows registered users (admin or member roles) to listen to audio files included in the calendar | Highly Needed | In Progress | High | Calendar
006 | Contains a calendar filled with generated readings and audio files | Highly Needed | In Progress | High | Calendar
007 | Allows users with admin role to add calendar events | Needed |  | Medium | Calendar
008 | Allows users with admin rolesto update or modify calendar events | Needed |  | Medium | Calendar
009 | Allows users with admin roles to delete calendar events | Needed |  | Medium | Calendar
010 | Filters the calendar if specific year is chosen by the user (admin or member roles) | Highly Needed | In Progress | High | Calendar
011 | Filters the calendar if specific month is chosen by the user (admin or member roles) | Highly Needed | In Progress | High | Calendar
012 | Updates the calendar display if CRUD function is performed by the user | Needed |  | Medium | Calendar
013 | Updates the system database if CRUD function is performed by the user | Highly Needed |  | High | Database
B. USER REQUIREMENTS
014 | User must have a username and a password to access the website | Needed | In Progress | Medium | Login
015 | User must access the website using the login page | Needed | In Progress | Medium | Login
016 | User can view the calendar | Highly Needed | In Progress | High | Calendar
017 | For users with admin role, he/she can perform create function in the calendar | Needed |  | Medium | Calendar
018 | For users with admin/member role, he/she can read the contents of the calendar | Highly Needed | In Progress | High | Calendar
019 | For users with admin role, he/she can perform update function in the calendar | Needed |  | Medium | Calendar
020 | For users with admin role, he/she can perform delete function in the calendar | Needed |  | Medium | Calendar
021 | User can click audio files provided in the calendar | Highly Needed | In Progress | High | Calendar
022 | User can click links | Highly Needed | In Progress | High | Calendar
023 | User can click buttons or tabs within the page | Highly Needed | In Progress | High | Calendar
024 | User can play the audio files provided in the calendar | Highly Needed | In Progress | High | Calendar
025 | User can listen to audio files provided in the calendar | Highly Needed | In Progress | High | Calendar
026 | User can view the calendar in a monthly basis | Highly Needed | In Progress | High | Calendar
027 | User can navigate through the different months of the year | Highly Needed | In Progress | High | Calendar
028 | User can choose a specific year to navigate | Highly Needed | In Progress | High | Calendar
029 | User can choose a specific month to navigate | Highly Needed | In Progress | High | Calendar
030 | User can view Weekday Readings | Highly Needed | In Progress | High | Calendar
031 | User can view Sunday Readings | Highly Needed | In Progress | High | Calendar