## Sheet1
Requirements Traceability Matrix
Project Name: | AngSalitaNgDiyos.com Liturgical Site
Project Type: | Website
Project Start Date: | 2015-01-12
Project End Date: | 2015-04-12
Project Adviser/s: | Mr. Joe Gene Quesada (Software Development)
Mr. Allan B. Cotecson (Quality Assurance)
Mr. Ernesto Boydon (Software Engineering)
Ms. Ma. Theresa Montemayor (Database Design and Management)
Project Manager: | Joshua C. Dimapilis
Requirement ID | Requirement Description | Requirement Type | Status | Priority | Software Module | Test Case Number | Tested In | Implemented In | Verification
A. SYSTEM REQUIREMENTS
001 | Provides a user-friendly interface for easier navigation | Highly Needed | In Progress | High | System Interface
002 | Provides a login page so that registered users can access the site | Highly Needed | In Progress | High | Login | 3.1.3
003 | Provides a sign up page to allow unregistered users to register and access the site | Highly Needed | In Progress | High | Login | 3.1.2
004 | Contains a calendar filled with generated readings and audio files | Highly Needed | In Progress | High | Calendar | 3.2.1
005 | Allows registered users (admin or member roles) to view the calendar and calendar events | Highly Needed | In Progress | High | Calendar | 3.2.1 3.3.3
006 | Does not allow unregistered users to view the calendar and calendar events | Highly Needed | In Progress | High | Calendar
007 | Filters the calendar if specific year is chosen by the user (admin or member roles) | Highly Needed | In Progress | High | Calendar | 3.3.4
008 | Filters the calendar if specific month is chosen by the user (admin or member roles) | Highly Needed | In Progress | High | Calendar | 3.3.4.1
009 | Allows registered users (admin or member roles) to listen to audio files included in the calendar | Highly Needed | In Progress | High | Calendar
010 | Allows users with admin role to add calendar events | Needed |  | Medium | Event
011 | Allows users with admin role to update or modify calendar events | Needed |  | Medium | Event
012 | Allows users with admin role to delete calendar events | Needed |  | Medium | Event
013 | Updates the calendar display if CRUD function is performed by the user | Needed |  | Medium | Event
014 | Updates the system database if CRUD function is performed by the user | Needed |  | Medium | Calendar
B. USER REQUIREMENTS
015 | Registered user must have a username and a password to access the website | Highly Needed | In Progress | HIgh | Login
016 | Registered user must access the website using the login page | Highly Needed | In Progress | High | Login | 3.1.3
017 | Registered user can view the calendar in a monthly basis | Highly Needed | In Progress | High | Calendar | 3.2.1
018 | Registered user can navigate through the different months/years of the calendar | Highly Needed | In Progress | High | Calendar | 3.3.4
019 | Registered user can choose a specific year to navigate | Highly Needed | In Progress | High | Calendar
020 | Registered user can choose a specific month to navigate | Highly Needed | In Progress | High | Calendar
021 | Registered user can view Weekday Readings | Highly Needed | In Progress | High | Calendar
022 | Registered user can view Sunday Readings | Highly Needed | In Progress | High | Calendar
023 | For users with admin role, he/she can perform create function in the calendar | Needed |  | Medium | Event
024 | For users with admin/member role, he/she can read the contents of the calendar | Highly Needed | In Progress | High | Calendar | 3.3.2
025 | For users with admin role, he/she can perform update function in the calendar | Needed |  | Medium | Event
026 | For users with admin role, he/she can perform delete function in the calendar | Needed |  | Medium | Calendar
027 | Registered user can click audio files provided in the calendar | Highly Needed | In Progress | High | Calendar
028 | Registered user can click links | Highly Needed | In Progress | High | Calendar
029 | Registered user can click buttons or tabs within the page | Highly Needed | In Progress | High | Calendar
030 | Registered user can play the audio files provided in the calendar | Highly Needed | In Progress | High | Calendar
031 | Registered user can listen to audio files provided in the calendar | Highly Needed | In Progress | High | Calendar